## TaskList
Task List Report - Preview / Review
| Team No. |  | 4 |  | Est. | Act. | Supervisor | Mr. Toh Da Jun
| Team Member |  | Eugene | M1 | 15 | 0 | From | 2017-08-14
|  |  | Yu Ming | M2 | 5 | 0 | To | 2017-08-17 |  | x
|  |  | Zhi Hao | M3 | 4 | 0 | Preview | 2017-08-14
|  |  | Guan Sheng | M4 | 8 | 0 | Review | 2017-08-17
| Preview | [7 empty] | Description of Task | Review
| No. | Title |  | Assign | Est. | Note / Comment |  |  |  | Done By | Act. | Note / Comment / Issue
| 1 | Different types of enemies |  | M1 | 1 |  |  |  | Different classes for different type of enemies
| 2 | Boundary check for enemies |  | M1 | 2 |  |  |  | Check if player stepped into a defined boundary | M1 | 2
| 3 | Enemy attributes |  | M1 | 1 |  |  |  | Giving enemies attributes such as health, attack and defense.
| 4 | Create attributes class |  | M2 | 1 |  |  |  | Creates class with attributes such as health, attack, defense, speed, level, experience and gold. And getters and setters for the variables | M2 | 1
| 5 | File manager |  | M4 | 1 |  |  |  | Loading and saving string from/to CSV file.
| 6 | Loading objects from CSV file |  | M4 | 2 |  |  |  | Pushing objects into respective lists after loading CSV file.
| 7 | Camera translation |  | M3 | 1 |  |  |  | Translating camera from point to point with delta time.
| 8 | Tower |  | M1 | 1 |  |  |  | Making towers owned by enemy or player. | M1 | 1
| 9 | Shooting towers |  | M1 | 1 |  |  |  | Having towers shoot at enemy or player. | M1 | 1
| 10 | Improve Sound manager |  | M2 | 2 |  |  |  | Improve sound manager to allow more options to control sounds played
| 11 | Converting enemy tower to player |  | M1 | 2 |  |  |  | When the tower health depletes to 0, the tower will belong to the player and attack the enemies.
| 12 | Billboard health bar for enemy |  | M1 | 1 |  |  |  | Render a health bar above the enemy. | M1 | 1
| 13 | Health bar for player |  | M1 | 1 |  |  |  | Render a health bar at the bottom left of the screen that represents the player health.
| 14 | Patrolling enemy |  | M1 | 2 |  |  |  | Enemy that will move according to waypoint(s) settled.
| 15 | Patrolling enemy returning back to base |  | M1 | 2 |  |  |  | Enemy will go back to waypoint if player is out of range.
| 16 | KO Count |  | M1 | 1 |  |  |  | Display amount of enemies killed on the right bottom.
| 17 | Inventory System |  | M4 | 3 |  |  |  | storing of items that the player can equip/ consume
| 18 | Particle manager |  | M3 | 3 |  |  |  | Manages/render particle effects
| 19 | Physics |  | M4 | 2 |  |  |  | implement physics in the program
| 20 | Implement Attribute class for enemy class |  | M2 | 1 |  |  |  | Implement attribute class into enemy class | M2 | 1
| 21 | Implement Attribute class for player class |  | M2 | 1 |  |  |  | Implement attribute class into player class | M2 | 1
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
| Total |  |  |  | 1 | [5 empty] | 0
| Comments for preview | [8 empty] | Comments for review
| (Any comment for this sprint?) | [8 empty] | (Any comment for this sprint?)
| Eugene |  |  |  | Yu Ming |  |  |  |  | Eugene |  |  | Yu Ming
| Zhi Hao |  |  |  | Guan Sheng |  |  |  |  | Zhi Hao |  |  | Guan Sheng
i
i
i
i
i
i
117
Note on F10: HONG CHRIS: Estimated volume of the task
Note on M10: HONG CHRIS: Actual volume after work done