## TaskList
Task List Report - Preview / Review
| Team No. |  | 4 |  | Est. | Act. | Supervisor | Mr. Toh Da Jun
| Team Member |  | Eugene | M1 | 1 | 0 | From | 2017-08-14
|  |  | Yu Ming | M2 | 0 | 0 | To | 2017-08-17 |  | x
|  |  | Zhi Hao | M3 | 0 | 0 | Preview | 2017-08-14
|  |  | Guan Sheng | M4 | 0 | 0 | Review | 2017-08-17
| Preview | [7 empty] | Description of Task | Review
| No. | Title |  | Assign | Est. | Note / Comment |  |  |  | Done By | Act. | Note / Comment / Issue
| 1 | Different types of enemies |  | M1 | 1 |  |  |  | Different classes for different type of enemies | M1 | 1
| 2 | Boundary check for enemies |  | M1 | 2 |  |  |  | Check if player stepped into a defined boundary | M1 | 2
| 3 | Enemy attributes |  | M1 | 1 |  |  |  | Giving enemies attributes such as health, attack and defense. | M1 | 1
| 4 | Player attributes |  | M2 | 1 |  |  |  | Giving player attributes such as health, magic power, attack, defense, speed, level, experience and gold. | M2 | 1
| 5 | File manager |  | M4 | 1 |  |  |  | Loading and saving string from/to CSV file. | M4 | 1
| 6 | Loading objects from CSV file |  | M4 | 2 |  |  |  | Pushing objects into respective lists after loading CSV file. | M4 | 2
| 7 | Camera translation |  | M3 | 1 |  |  |  | Translating camera from point to point with delta time. | M3 | 1
| 8 | Tower |  | M1 | 1 |  |  |  | Making towers owned by enemy or player. | M1 | 1
| 9 | Shooting towers |  | M1 | 1 |  |  |  | Having towers shoot at enemy or player. | M1 | 1
| 10 | Sound manager |  | M2 | 2 |  |  |  | Play sound in 2D and 3D
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
| Total |  |  |  | 1 | [5 empty] | 1
| Comments for preview | [8 empty] | Comments for review
| (Any comment for this sprint?) | [8 empty] | (Any comment for this sprint?)
| Eugene |  |  |  | Yu Ming |  |  |  |  | Eugene |  |  | Yu Ming
| Zhi Hao |  |  |  | Guan Sheng |  |  |  |  | Zhi Hao |  |  | Guan Sheng
i
i
i
i
i
i
117
Note on F10: HONG CHRIS: Estimated volume of the task
Note on M10: HONG CHRIS: Actual volume after work done