## Sheet1
Task Name | Start | End | Allocated to | Duration (days)
Map Editor; creating objects on map based on user input. | 2017-08-14 | 2017-08-16 | Lai Wei Jing, Eugene [Team Leader] | 2
Enemy Turret; converting enemy turret to player turret. | 2017-08-14 | 2017-08-16 | Lai Wei Jing, Eugene [Team Leader] | 2
Boundary check for enemy; a check to see if player stepped into a certain boundary of enemy | 2017-08-14 | 2017-08-16 | Lai Wei Jing, Eugene [Team Leader] | 2
Cinematic Class; making another camera for cinematic use. | 2017-08-14 | 2017-08-16 | Chan Zhihao [Team Member #1] | 2
Particle Manager; creating particle objects | 2017-08-14 | 2017-08-16 | Chan Zhihao [Team Member #1] | 2
Melee; trying out the concept of creating short projectile to represent melee. | 2017-08-14 | 2017-08-16 | Chan Zhihao [Team Member #1] | 2
Write and Reading of CSV Files | 2017-08-14 | 2017-08-16 | Lim Guan Sheng, Marcus [Team Member #2] | 2
Inventory Class; having array to save objects. | 2017-08-14 | 2017-08-16 | Lim Guan Sheng, Marcus [Team Member #2] | 2
Equipment Class; having array to save objects. | 2017-08-14 | 2017-08-16 | Lim Guan Sheng, Marcus [Team Member #2] | 2
Attribute Class | 2017-08-14 | 2017-08-16 | Kwong Yu Ming [Team Member #3] | 2
OBJ for enemies | 2017-08-14 | 2017-08-16 | Kwong Yu Ming [Team Member #3] | 2
TGA for enemies | 2017-08-14 | 2017-08-16 | Kwong Yu Ming [Team Member #3] | 2
Gamepad Manager; experimenting xinput library. | 2017-08-17 | 2017-08-18 | Kwong Yu Ming [Team Leader] | 1
Doing animation with modelstack for enemies. | 2017-08-17 | 2017-08-18 | Kwong Yu Ming [Team Leader] | 1
Link attribute class to player and enemies. | 2017-08-17 | 2017-08-18 | Kwong Yu Ming [Team Leader] | 1
Exploring camera vector; translating camera from place to place | 2017-08-17 | 2017-08-18 | Chan Zhihao [Team Member #1] | 1
Optimising particles; rendering and creating only a certain amount of particles | 2017-08-17 | 2017-08-18 | Chan Zhihao [Team Member #1] | 1
Creating melee class. | 2017-08-17 | 2017-08-18 | Chan Zhihao [Team Member #1] | 1
Creating a variety of equipment. | 2017-08-17 | 2017-08-18 | Lim Guan Sheng, Marcus [Team Member #2] | 1
Linking attribute to equipment. | 2017-08-17 | 2017-08-18 | Lim Guan Sheng, Marcus [Team Member #2] | 1
Finding TGA for equipment. | 2017-08-17 | 2017-08-18 | Lim Guan Sheng, Marcus [Team Member #2] | 1
Enemy A.I pathfinding; create 36 nodes around enemy to check. | 2017-08-17 | 2017-08-18 | Lai Wei Jing, Eugene [Team Member #3] | 1
Locking target to nearest enemy. | 2017-08-17 | 2017-08-18 | Lai Wei Jing, Eugene [Team Member #3] | 1
Aspect ratio scaling. | 2017-08-17 | 2017-08-18 | Lai Wei Jing, Eugene [Team Member #3] | 1
Equipping and discard items in inventory. | 2017-08-21 | 2017-08-23 | Lim Guan Sheng, Marcus [Team Leader] | 2
Saving inventory and equipment. | 2017-08-21 | 2017-08-23 | Lim Guan Sheng, Marcus [Team Leader] | 2
Finding TGA for inventory items. | 2017-08-21 | 2017-08-23 | Lim Guan Sheng, Marcus [Team Leader] | 2
Creating cooldown for melee. | 2017-08-21 | 2017-08-23 | Chan Zhihao [Team Member #1] | 2
Combo system for melee. | 2017-08-21 | 2017-08-23 | Chan Zhihao [Team Member #1] | 2
Creating multiple types of cinematic options; panning to target and panning to different destinations. | 2017-08-21 | 2017-08-23 | Chan Zhihao [Team Member #1] | 2
Creating a Debugger; cout only when a boolean is true. | 2017-08-21 | 2017-08-23 | Lai Wei Jing, Eugene [Team Member #2] | 2
Creating a Text Manager that prints different styles of text on screen. | 2017-08-21 | 2017-08-23 | Lai Wei Jing, Eugene [Team Member #2] | 2
Scene Manager to switch scene properly; re-initialising a new scene when switching. | 2017-08-21 | 2017-08-23 | Lai Wei Jing, Eugene [Team Member #2] | 2
AABB for objects. | 2017-08-21 | 2017-08-23 | Kwong Yu Ming [Team Member #3] | 2
Linking attribute to player. | 2017-08-21 | 2017-08-23 | Kwong Yu Ming [Team Member #3] | 2
Linking player attribute with enemy attribute when checking for damage. | 2017-08-21 | 2017-08-23 | Kwong Yu Ming [Team Member #3] | 2
Level 03 | 2017-08-24 | 2017-08-25 | Chan Zhihao [Team Leader] | 1
User Interface | 2017-08-24 | 2017-08-25 | Chan Zhihao [Team Leader] | 1
Optimising particles and cinematic class; prevent memory leak. | 2017-08-24 | 2017-08-25 | Chan Zhihao [Team Leader] | 1
Tutorial and Level 01 | 2017-08-24 | 2017-08-25 | Lai Wei Jing, Eugene [Team Member #1] | 1
User Interface | 2017-08-24 | 2017-08-25 | Lai Wei Jing, Eugene [Team Member #1] | 1
Real-time controls changer. | 2017-08-24 | 2017-08-25 | Lai Wei Jing, Eugene [Team Member #1] | 1
Level 04 | 2017-08-24 | 2017-08-25 | Lim Guan Sheng, Marcus [Team Member #2] | 1
User Interface | 2017-08-24 | 2017-08-25 | Lim Guan Sheng, Marcus [Team Member #2] | 1
Village | 2017-08-24 | 2017-08-25 | Lim Guan Sheng, Marcus [Team Member #2] | 1
Level 02 | 2017-08-24 | 2017-08-25 | Kwong Yu Ming [Team Member #3] | 1
Quest Manager | 2017-08-24 | 2017-08-25 | Kwong Yu Ming [Team Member #3] | 1
User Interface | 2017-08-24 | 2017-08-25 | Kwong Yu Ming [Team Member #3] | 1
Error checking | 2017-08-28 | 2017-08-30 | Lai Wei Jing, Eugene [Team Leader] | 2
Documentation | 2017-08-28 | 2017-08-30 | Lai Wei Jing, Eugene [Team Leader] | 2
Test play | 2017-08-28 | 2017-08-30 | Lai Wei Jing, Eugene [Team Leader] | 2
Error checking | 2017-08-28 | 2017-08-30 | Chan Zhihao [Team Member #1] | 2
Documentation | 2017-08-28 | 2017-08-30 | Chan Zhihao [Team Member #1] | 2
Test play | 2017-08-28 | 2017-08-30 | Chan Zhihao [Team Member #1] | 2
Error checking | 2017-08-28 | 2017-08-30 | Lim Guan Sheng, Marcus [Team Member #2] | 2
Documentation | 2017-08-28 | 2017-08-30 | Lim Guan Sheng, Marcus [Team Member #2] | 2
Test play | 2017-08-28 | 2017-08-30 | Lim Guan Sheng, Marcus [Team Member #2] | 2
Error checking | 2017-08-28 | 2017-08-30 | Kwong Yu Ming [Team Member #3] | 2
Documentation | 2017-08-28 | 2017-08-30 | Kwong Yu Ming [Team Member #3] | 2
Test play | 2017-08-28 | 2017-08-30 | Kwong Yu Ming [Team Member #3] | 2